## Sheet1
Tasks | Estimated Hours | Description
Xamarin Project Setup | 1
R&D on Shibboleth for authentication | 2
R&D on Acoustic Echo Cancellation API to remove echoes and noise | 6
R&D Recording and conversion in xamarin | 6
Mobile Implementation
Splash Screen Design & implementation | 5
Signin screen implementation | 4
Forgot password implementation | 3
Reset Password | 3
Search Patient or My Patient with search result Screen | 15
Notification implementation | ?? | Not sure about notifications now.
Patient Information screen | 5
Existing Recording screen | 15
Recording Screen | 20
Save Recording, Convert & upload to API | 6
Help Screen | 5
IOS File generation | 6
WebSite/Admin Interface
Project Setup & Website design implementation | 4
User Login | 6
Forgot Password | 3
Manage Users
Create/Update Users | 8
Delete/Inactive users | 2
View Users with filters | 8
Select Patient and view recording(s) | 8
Listen Recording | 4
Recording Report |  | Need more details. Not sure what is included in report
Patient Management
Insert/Update Patient information | 8 | Need list of fields/data to be inserted
Delete/Inactive Patient | 2
List of Patients with filters | 6
Patient Audio Recording Management
View Patient Audio Recording | 4
Delete Audio recording | 1
Patient Audio Recording Transacripts
View transcripts with Patient name/number | 6 | Need more detail on this. Mobile version will generate transcripts or some backend job will do against uploaded audio??
Coordination with API development team | 15 | These are hours if coordination is required with API team

## IOS
Mobile Implementation | Estimated Hours | Estimated Amount (In $15/hr )
Splash Screen Design & implementation | 10 | 150
Signin screen implementation | 8 | 120
Forgot password implementation | 10 | 150
Reset Password | 6 | 90
Search Patient or My Patient with search result Screen | 30 | 450
Notification implementation | 40 | 600
Patient Information screen | 15 | 225
Existing Recording screen | 30 | 450
Recording Screen | 40 | 600
Save Recording, Convert & upload to API | 15 | 225
Help Screen | 15 | 225
IOS File generation | 16 | 240
Total: | 235 | 3525